Project Planning Phase

Project Planning Template (Product Backlog, Sprint Planning, Stories, Story points)

| Date | 08 February 2026 |
| --- | --- |
| Team ID | LTVIP2026TMIDS66040 |
| Project Name | IntelliSQL: Intelligent SQL Querying with LLMs Using Gemini Pro |
| Maximum Marks | 5 Marks |

Product Backlog, Sprint Schedule, and Estimation (4 Marks) Use the below template to create product backlog and sprint schedule

| Sprint | Functional Requirement (Epic) | User Story Number | User Story / Task | Story Points | Priority | Team Members |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | Authentication & DB Setup | USN-1 | User registration and login module | 3 | High | 5 |
| Sprint-1 | Authentication & DB Setup | USN-2 | Secure database connection (MySQL/PostgreSQL) | 5 | High | 5 |
| Sprint-1 | Authentication & DB Setup | USN-3 | Display database schema and tables | 5 | Low | 5 |
| Sprint-1 | UI Development | USN-4 | Dashboard for entering natural language queries | 7 | Medium | 5 |
| Sprint-2 | NL to SQL Engine | USN-5 | Convert natural language to SQL using Gemini Pro | 8 | High | 5 |
| Sprint-2 | Query Processing | USN-6 | Validate generated SQL queries | 5 | High | 5 |
| Sprint-2 | Query Execution | USN-7 | Execute SQL and display results | 5 | High | 5 |
| Sprint | Functional Requirement (Epic) | User Story Number | User Story / Task | Story Points | Priority | Team Members |
| Sprint-2 | Error Handling | USN-8 | Provide meaningful error messages | 2 | Medium | 5 |
| Sprint-3 | Optimization | USN-9 | Optimize generated SQL queries | 6 | Medium | 5 |
| Sprint-3 | Visualization | USN-10 | Display results in charts/graphs | 6 | Medium | 5 |
| Sprint-3 | History Feature | USN-11 | Maintain query history | 4 | Low | 5 |
| Sprint-3 | Security | USN-12 | Prevent SQL injection and secure execution | 4 | High | 5 |
| Sprint-4 | Testing | USN-13 | Unit and integration testing | 6 | High | 5 |
| Sprint-4 | Performance Testing | USN-14 | Test system with large datasets | 5 | Medium | 5 |
| Sprint-4 | Deployment | USN-15 | Deploy application on cloud/local server | 5 | High | 5 |
| Sprint-4 | Documentation | USN-16 | Prepare technical documentation and user manual | 4 | Medium | 5 |

# Project Tracker, Velocity & Burndown Chart: (4 Marks)

| Sprint | Total Story Points | Duration | Sprint Start Date | Sprint End Date (Planned) | Story Points Completed (as on Planned End Date) | Sprint Release Date (Actual) |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | 20 | 7 Days | 20 Feb 2025 | 26 Feb 2025 | 20 | 26 Feb 2025 |
| Sprint | Total Story Points | Duration | Sprint Start Date | Sprint End Date (Planned) | Story Points Completed (as on Planned End Date) | Sprint Release Date (Actual) |
| Sprint-2 | 20 | 7 Days | 28 Feb 2025 | 06 Mar 2025 | 20 | 06 Mar 2025 |
| Sprint-3 | 20 | 7 Days | 08 Mar 2025 | 14 Mar 2025 | 20 | 14 Mar 2025 |
| Sprint-4 | 20 | 7 Days | 16 Mar 2025 | 22 Mar 2025 | 20 | 22 Mar 2025 |

Velocity:

Imagine we have a 10-day sprint duration, and the velocity of the team is 20 (points per sprint). Let’s calculate the team’s average velocity (AV) per iteration unit (story points per day)

Burndown Chart:

The Burndown Chart represents remaining story points versus time. Each sprint starts with 20 story points. Points reduce daily as tasks are completed, reaching zero by the sprint end date.

https://www.visual-paradigm.com/scrum/scrum-burndown-chart/ https://www.atlassian.com/agile/tutorials/burndown-charts

Reference:

https://www.atlassian.com/agile/project-management

https://www.atlassian.com/agile/tutorials/how-to-do-scrum-with-jira-software https://www.atlassian.com/agile/tutorials/epics https://www.atlassian.com/agile/tutorials/sprints

https://www.atlassian.com/agile/project-management/estimation https://www.atlassian.com/agile/tutorials/burndown-charts